## Clarification Log
Clarification Log
Document Title: Clarification Log
Activity ID: M1.5
Date: 12-04-2025
Project Team ID: TP802 – S2 – 3
Project Team Name: Team - 3
Date | Question/Clarification Needed | Response/Decision | Status
Date | Question/Clarification Needed | Response/Decision | Status
2025-04-12 | How to handle API rate limits platforms? | Use setInterval in Express.js for periodic API calls. Avoid advanced scheduling tools | Completed
2025-04-12 | Where to store social media data? | Store all data in a single Supabase table | Completed
2025-04-12 | How to implement real-time updates? | Use Supabase Realtime for live updates.React Query will handle data fetching on the frontend | Completed
2025-04-12 | How to manage user authentication? | Use Supabase Auth with email-based login | Pending
2025-04-12 | How to track campaigns? | Add a campaigns table in Supabase with basic fields: name, hashtags, start_date, end_date | Pending
2025-04-12 | What metrics to calculate ROI | (Engagement Rates x Conversion Rate) - Campaign Cost | Pending
2025-04-12 | How to manage frontend state? | Use React Query for server state management | Pending
2025-04-12 | How to handle API errors? | Log errors in the console and retry failed requests using error handling logic in Express.js | Pending
2025-04-12 | How to monitor the system? | Use Supabase logs for backend monitoring and browser console logs for frontend debugging. | Pending
2025-04-12 | What is the backup strategy? | Enable automatic daily backups in Supabase | Pending
2025-04-12 | How to scale the application if usage grows? | Manually upgrade Supabase’s plan as needed based on usage trends. | Pending